## Wind Chart
[6 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[6 empty] | 18INR0073 | Sweetwater 1 repower | Nolan | 2024-11-30 | 2002-10-23 | Wind | WT | 3 | 2024 | No
[6 empty] | 22INR0301 | Fortuna Wind | Jack | 2026-07-01 | 2024-08-08 | Wind | WT | 295.3 | 2026 | No
[6 empty] | 16INR0112 | Loma Pinta Wind | La Salle | 2026-12-31 | 2017-12-13 | Wind | WT | 197.01 | 2026 | No
[6 empty] | 26INR0622 | Buffalo Gap 1 Wind Repower | Taylor | 2027-02-01 | 2005-02-28 | Wind | WT | 120.23 | 2027 | Yes
[6 empty] | 26INR0625 | Buffalo Gap 2 Wind Repower | Nolan | 2027-02-01 | 2005-02-28 | Wind | WT | 231.49 | 2027 | Yes
[6 empty] | 26INR0626 | Buffalo Gap 3 Wind Repower | Taylor | 2027-02-01 | 2005-02-28 | Wind | WT | 168.45 | 2027 | Yes
[6 empty] | 27INR0367 | Goat Mountain Wind-Repower | Sterling | 2027-03-01 | 2026-02-20 | Wind | WT | 303.2 | 2027 | Yes
[6 empty] | 25INR0018 | Yellow Cat Wind | Navarro | 2027-03-05 | 2024-07-09 | Wind | WT | 262 | 2027 | Yes
[6 empty] | 26INR0647 | Wake Wind Energy Repower | Crosby | 2027-06-04 | 2014-02-28 | Wind | WT | 252.5 | 2027 | No
[6 empty] | 23INR0637 | Goodnight Wind II | Armstrong | 2027-06-06 | 2019-08-18 | Wind | WT | 261.1 | 2027 | Yes
[6 empty] | 24INR0291 | Rubicon Alpha Wind | Haskell | 2027-07-31 | 2024-05-08 | Wind | WT | 222.6 | 2027 | Yes
[6 empty] | 21INR0263 | Monarch Creek Wind | Throckmorton | 2027-09-17 | 2020-08-24 | Wind | WT | 283.4 | 2027 | Yes
[6 empty] | 25INR0494 | Willow Beach Wind | Brazoria | 2027-10-01 | 2025-06-16 | Wind | WT | 202.33 | 2027 | No
[6 empty] | 23INR0561 | Cascabel Wind 2 | Zapata | 2027-12-01 | 2025-05-23 | Wind | WT | 197.75 | 2027 | Yes
[6 empty] | 24INR0424 | Cascabel Wind 1 | Zapata | 2027-12-01 | 2025-05-23 | Wind | WT | 197.75 | 2027 | Yes
[6 empty] | 24INR0505 | Corralitos Wind 1 | Zapata | 2027-12-01 | 2025-06-19 | Wind | WT | 196.1 | 2027 | Yes
[6 empty] | 20INR0247 | Water Valley Wind Energy | Tom Green | 2027-12-15 | 2025-03-17 | Wind | WT | 180 | 2027 | Yes
[6 empty] | 24INR0506 | Corralitos Wind 2 | Zapata | 2027-12-31 | 2025-06-19 | Wind | WT | 195.4 | 2027 | Yes
[6 empty] | 27INR0004 | Dundee West Wind | Wilbarger | 2027-12-31 | 2025-02-21 | Wind | WT | 146.49 | 2027 | Yes
[6 empty] | 27INR0005 | Dundee East A Wind | Baylor | 2027-12-31 | 2025-02-21 | Wind | WT | 524 | 2027 | Yes
[6 empty] | 27INR0011 | Dundee East B Wind | Baylor | 2027-12-31 | 2025-02-21 | Wind | WT | 261.45 | 2027 | Yes
[6 empty] | 27INR0056 | Laurel Wind Energy Center | Pecos | 2027-12-31 | 2024-10-25 | Wind | WT | 306.6 | 2027 | Yes
[6 empty] | 26INR0021 | Crossroads Wind | Victoria | 2028-02-28 | 2024-07-24 | Wind | WT | 277.38 | 2028 | Yes
Month/Year | Cumulative operational, No FS, and FS Posted | Cumulative MW Operational | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Small Generator
2026-09-20 | 41211.05 | 41208.05 | 0 | 3 | 0
2026-10-20 | 41211.05 | 41208.05 | 0 | 3 | 0
2026-11-20 | 41211.05 | 41208.05 | 0 | 3 | 0
2026-12-20 | 41703.36 | 41208.05 | 0 | 495.31 | 0
2027-01-20 | 41703.36 | 41208.05 | 0 | 495.31 | 0
2027-02-20 | 42223.53 | 41208.05 | 520.17 | 495.31 | 0
2027-03-20 | 42788.73 | 41208.05 | 1085.37 | 495.31 | 0
2027-04-20 | 42788.73 | 41208.05 | 1085.37 | 495.31 | 0
2027-05-20 | 42788.73 | 41208.05 | 1085.37 | 495.31 | 0
2027-06-20 | 43302.33 | 41208.05 | 1346.47 | 747.81 | 0
2027-07-20 | 43524.93 | 41208.05 | 1569.07 | 747.81 | 0
2027-08-20 | 43524.93 | 41208.05 | 1569.07 | 747.81 | 0
2027-09-20 | 43808.33 | 41208.05 | 1852.47 | 747.81 | 0
2027-10-20 | 44010.66 | 41208.05 | 1852.47 | 950.14 | 0
2027-11-20 | 44010.66 | 41208.05 | 1852.47 | 950.14 | 0
2027-12-20 | 46216.2 | 41208.05 | 4058.01 | 950.14 | 0
2028-01-20 | 46216.2 | 41208.05 | 4058.01 | 950.14 | 0
2028-02-20 | 46493.58 | 41208.05 | 4335.39 | 950.14 | 0

## Solar Chart
[6 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[6 empty] | 23INR0487 | Brightside Solar Alt POI | Live Oak | 2026-08-14 | 2020-06-11 | Solar | PV | 50 | 2026 | Yes
[6 empty] | 19INR0103 | Rodeo Solar | Andrews | 2026-11-30 | 2019-08-20 | Solar | PV | 200 | 2026 | Yes
[6 empty] | 21INR0334 | Nightfall Solar | Uvalde | 2026-12-31 | 2023-10-26 | Solar | PV | 180.87 | 2026 | Yes
[6 empty] | 21INR0421 | Armadillo Solar | Navarro | 2026-12-31 | 2021-02-02 | Solar | PV | 150.48 | 2026 | Yes
[6 empty] | 22INR0262 | Sequoia II Solar | Callahan | 2027-01-28 | 2023-08-29 | Solar | PV | 417.47 | 2027 | Yes
[6 empty] | 21INR0362 | Oystercatcher Solar | Ellis | 2027-01-29 | 2021-08-20 | Solar | PV | 198.43 | 2027 | No
[6 empty] | 23INR0244 | Tiger Solar | Jones | 2027-02-26 | 2024-10-30 | Solar | PV | 250.9 | 2027 | Yes
[6 empty] | 29INR0015 | Funston Solar | Jones | 2027-02-26 | 2024-10-23 | Solar | PV | 351.1 | 2027 | Yes
[6 empty] | 22INR0559 | Honeycomb Solar SLF | Bee | 2027-02-27 | 2023-05-01 | Solar | PV | 61.4 | 2027 | Yes
[6 empty] | 21INR0253 | Ulysses Solar | Coke | 2027-03-17 | 2022-10-03 | Solar | PV | 151.2 | 2027 | Yes
[6 empty] | 24INR0137 | Eagle Springs Solar | Delta | 2027-03-29 | 2024-04-17 | Solar | PV | 77.21 | 2027 | Yes
[6 empty] | 22INR0437 | TORMES SOLAR | Navarro | 2027-03-31 | 2024-04-10 | Solar | PV | 356.6 | 2027 | Yes
[6 empty] | 24INR0154 | Lupinus Solar 2 | Franklin | 2027-04-03 | 2025-03-04 | Solar | PV | 242.31 | 2027 | Yes
[6 empty] | 25INR0199 | Bonham Solar SLF | Limestone | 2027-04-06 | 2024-08-07 | Solar | PV | 138.4 | 2027 | Yes
[6 empty] | 23INR0235 | Hoyte Solar | Milam | 2027-04-15 | 2022-10-14 | Solar | PV | 206.75 | 2027 | Yes
[6 empty] | 25INR0232 | Isaac Solar | Matagorda | 2027-04-15 | 2023-10-18 | Solar | PV | 50.73 | 2027 | Yes
[6 empty] | 23INR0027 | Clear Fork Creek Solar | Wilson | 2027-04-29 | 2021-11-23 | Solar | PV | 602.02 | 2027 | Yes
[6 empty] | 23INR0207 | El Patrimonio Solar | Bexar | 2027-04-29 | 2023-12-11 | Solar | PV | 152.32 | 2027 | Yes
[6 empty] | 21INR0371 | Pecan Prairie South | Leon | 2027-05-01 | 2021-02-21 | Solar | PV | 132.98 | 2027 | Yes
[6 empty] | 21INR0428 | Pecan Prairie North | Leon | 2027-05-01 | 2021-02-26 | Solar | PV | 324.11 | 2027 | Yes
[6 empty] | 22INR0454 | Wallace Solar | Culberson | 2027-05-14 | 2022-02-07 | Solar | PV | 36 | 2027 | Yes
[6 empty] | 24INR0188 | Tehuacana Creek Solar | Navarro | 2027-05-18 | 2024-11-25 | Solar | PV | 505.43 | 2027 | Yes
[6 empty] | 21INR0341 | Space City Solar | Wharton | 2027-06-01 | 2025-12-11 | Solar | PV | 366 | 2027 | Yes
[6 empty] | 25INR0102 | Austin Bayou Solar | Brazoria | 2027-06-01 | 2023-11-15 | Solar | PV | 502.48 | 2027 | Yes
[6 empty] | 23INR0045 | Caney Creek Solar | Van Zandt | 2027-06-21 | 2021-12-29 | Solar | PV | 121.04 | 2027 | Yes
[6 empty] | 26INR0524 | Fagus Solar Park 3 SLF | Childress | 2027-06-28 | 2019-02-21 | Solar | PV | 169.59 | 2027 | Yes
[6 empty] | 23INR0289 | Skull Creek Solar | Anderson | 2027-06-30 | 2024-05-20 | Solar | PV | 136.98 | 2027 | No
[6 empty] | 25INR0225 | Lucy Solar | Concho | 2027-06-30 | 2024-05-29 | Solar | PV | 352.21 | 2027 | Yes
[6 empty] | 25INR0368 | Echols Grove Solar | Lamar | 2027-06-30 | 2024-07-06 | Solar | PV | 201.56 | 2027 | Yes
[6 empty] | 23INR0231 | Hoke Solar | Gonzales | 2027-07-05 | 2022-04-25 | Solar | PV | 95.29 | 2027 | Yes
[6 empty] | 26INR0269 | Moccasin Solar | Stonewall | 2027-07-06 | 2024-09-04 | Solar | PV | 603.59 | 2027 | Yes
[6 empty] | 25INR0081 | SanPat Solar I | San Patricio | 2027-07-08 | 2023-10-18 | Solar | PV | 308.88 | 2027 | Yes
[6 empty] | 25INR0164 | Star Dairy Solar | Lamar | 2027-07-12 | 2024-12-09 | Solar | PV | 115.61 | 2027 | No
[6 empty] | 21INR0520 | Yellow Viking Solar | Somervell | 2027-07-13 | 2022-10-25 | Solar | PV | 171.13 | 2027 | Yes
[6 empty] | 25INR0052 | SanPat Solar II | San Patricio | 2027-07-22 | 2023-10-18 | Solar | PV | 256.23 | 2027 | Yes
[6 empty] | 26INR0155 | Ross Solar | Refugio | 2027-07-31 | 2024-06-27 | Solar | PV | 1025.57 | 2027 | No
[6 empty] | 25INR0382 | HappyDogSolar | Milam | 2027-08-04 | 2024-12-16 | Solar | PV | 85.54 | 2027 | No
[6 empty] | 23INR0086 | Hanson Solar | Coleman | 2027-08-17 | 2023-09-20 | Solar | PV | 398.83 | 2027 | Yes
[6 empty] | 26INR0718 | PHOTON SOLAR REPOWERING | Wharton | 2027-08-17 | 2021-02-25 | Solar | PV | 0 | 2027 | No
[6 empty] | 22INR0342 | Matagorda Solar | Matagorda | 2027-08-25 | 2022-06-08 | Solar | PV | 101 | 2027 | Yes
[6 empty] | 23INR0349 | Tokio Solar | McLennan | 2027-08-25 | 2023-11-06 | Solar | PV | 170.45 | 2027 | Yes
[6 empty] | 24INR0106 | Payne Battlecreek | Hill | 2027-08-25 | 2024-02-23 | Solar | PV | 84.99 | 2027 | No
[6 empty] | 23INR0040 | Dori BQ Solar | Harris | 2027-08-30 | 2022-12-01 | Solar | PV | 50.42 | 2027 | No
[6 empty] | 16INR0049 | Nazareth Solar | Castro | 2027-08-31 | 2026-03-05 | Solar | PV | 203 | 2027 | Yes
[6 empty] | 21INR0210 | Adamstown Solar | Wilbarger | 2027-08-31 | 2024-12-04 | Solar | PV | 250.88 | 2027 | Yes
[6 empty] | 22INR0605 | Camino Santiago Solar | Milam | 2027-09-01 | 2024-12-06 | Solar | PV | 196.3 | 2027 | Yes
[6 empty] | 24INR0150 | Lupinus Solar 1 | Franklin | 2027-09-13 | 2025-06-26 | Solar | PV | 162.31 | 2027 | Yes
[6 empty] | 27INR0434 | Lyra Solar | Borden | 2027-09-15 | 2025-07-01 | Solar | PV | 500 | 2027 | Yes
[6 empty] | 21INR0031 | Indigo Solar | Fisher | 2027-09-17 | 2020-09-15 | Solar | PV | 150 | 2027 | Yes
[6 empty] | 23INR0150 | Cradle Solar | Brazoria | 2027-09-17 | 2023-03-15 | Solar | PV | 200.85 | 2027 | Yes
[6 empty] | 25INR0204 | Cedar Range Solar | Hopkins | 2027-09-17 | 2025-07-02 | Solar | PV | 150.64 | 2027 | No
[6 empty] | 26INR0380 | Pepper Solar Farm | McLennan | 2027-09-20 | 2025-06-23 | Solar | PV | 120.72 | 2027 | Yes
[6 empty] | 26INR0409 | Lucky 7 Solar | Hopkins | 2027-09-20 | 2025-08-13 | Solar | PV | 101.35 | 2027 | Yes
[6 empty] | 27INR0049 | Darkwood Solar | Comanche | 2027-09-20 | 2025-11-05 | Solar | PV | 152.02 | 2027 | Yes
[6 empty] | 21INR0391 | Grandslam Solar | Atascosa | 2027-10-01 | 2021-01-29 | Solar | PV | 121.89 | 2027 | No
[6 empty] | 24INR0167 | OCI SunRoper | Wharton | 2027-10-01 | 2025-07-10 | Solar | PV | 265.1 | 2027 | Yes
[6 empty] | 24INR0326 | Blarney Solar | Hopkins | 2027-10-01 | 2024-04-22 | Solar | PV | 81.46 | 2027 | No
Month/Year | Cumulative operational, No FS, and FS Posted | Cumulative MW Operational | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Small Generator | 27INR0438 | Wisdom Solar SLF | Pecos | 2027-10-06 | 2026-03-18 | Solar | PV | 299.37 | 2027 | No
2026-09-20 | 41975.99 | 41925.99 | 50 | 0 | 0 | 23INR0056 | Caliche Mound Solar | Deaf Smith | 2027-10-26 | 2023-10-12 | Solar | PV | 406.6 | 2027 | Yes
2026-10-20 | 41975.99 | 41925.99 | 50 | 0 | 0 | 26INR0241 | Sol Marina SLF Energy Center | Ellis | 2027-10-29 | 2025-04-25 | Solar | PV | 171.09 | 2027 | Yes
2026-11-20 | 42175.99 | 41925.99 | 250 | 0 | 0 | 26INR0130 | Elm Flats Solar SLF | Navarro | 2027-11-01 | 2025-11-21 | Solar | PV | 125.84 | 2027 | Yes
2026-12-20 | 42507.34 | 41925.99 | 581.35 | 0 | 0 | 27INR0198 | Musgravite Solar | Henderson | 2027-11-01 | 2025-05-20 | Solar | PV | 100.6 | 2027 | Yes
2027-01-20 | 43123.24 | 41925.99 | 998.82 | 198.43 | 0 | 22INR0220 | Lamkin Solar | Comanche | 2027-11-08 | 2025-03-06 | Solar | PV | 101.5 | 2027 | Yes
2027-02-20 | 43786.64 | 41925.99 | 1662.22 | 198.43 | 0 | 25INR0281 | Cosper Solar | Bell | 2027-11-12 | 2025-07-31 | Solar | PV | 148.16 | 2027 | Yes
2027-03-20 | 44371.65 | 41925.99 | 2247.23 | 198.43 | 0 | 26INR0621 | Juno 3 Solar | Borden | 2027-11-30 | 2025-07-01 | Solar | PV | 500 | 2027 | Yes
2027-04-20 | 45764.18 | 41925.99 | 3639.76 | 198.43 | 0 | 27INR0500 | Antila Solar | Borden | 2027-11-30 | 2025-08-13 | Solar | PV | 500 | 2027 | Yes
2027-05-20 | 46762.7 | 41925.99 | 4638.28 | 198.43 | 0 | 25INR0422 | Waterloo Solar 1 | Bastrop | 2027-12-01 | 2024-09-04 | Solar | PV | 200.64 | 2027 | No
2027-06-20 | 48612.56 | 41925.99 | 6351.16 | 335.41 | 0 | 24INR0161 | Miranda Solar Project | McMullen | 2027-12-06 | 2024-07-16 | Solar | PV | 261.67 | 2027 | Yes
2027-07-20 | 51188.86 | 41925.99 | 7786.28 | 1476.59 | 0 | 24INR0298 | Leighton Solar | Limestone | 2027-12-06 | 2024-05-28 | Solar | PV | 181 | 2027 | Yes
2027-08-20 | 52533.97 | 41925.99 | 8910.44 | 1697.54 | 0 | 24INR0038 | Jaguar Solar | McLennan | 2027-12-11 | 2022-09-12 | Solar | PV | 300.87 | 2027 | Yes
2027-09-20 | 54268.16 | 41925.99 | 10493.99 | 1848.18 | 0 | 24INR0201 | Short Creek Solar | Wichita | 2027-12-17 | 2024-10-02 | Solar | PV | 627.81 | 2027 | Yes
2027-10-20 | 55613.67 | 41925.99 | 11336.78 | 2350.9 | 0 | 24INR0186 | Rowdy Creek Solar | Lamar | 2027-12-29 | 2025-05-02 | Solar | PV | 351.78 | 2027 | Yes
2027-11-20 | 57089.77 | 41925.99 | 12812.88 | 2350.9 | 0 | 27INR0313 | Spindletop Solar | Nacogdoches | 2027-12-29 | 2025-12-29 | Solar | PV | 286.4 | 2027 | Yes
2027-12-20 | 61204.78 | 41925.99 | 16138.87 | 3139.92 | 0 | 25INR0304 | Flying Kite Solar | Zavala | 2027-12-30 | 2024-10-02 | Solar | PV | 80.38 | 2027 | No
2028-01-20 | 62383.45 | 41925.99 | 17001.04 | 3456.42 | 0 | 22INR0455 | Blue Sky Sol | Crockett | 2027-12-31 | 2022-02-01 | Solar | PV | 101.2 | 2027 | Yes
2028-02-20 | 62634.13 | 41925.99 | 17101.04 | 3607.1 | 0 | 23INR0057 | Duffy Solar | Matagorda | 2027-12-31 | 2023-04-12 | Solar | PV | 502.46 | 2027 | Yes
[6 empty] | 24INR0404 | Tres Rios Ranch Solar | Upton | 2027-12-31 | 2025-12-30 | Solar | PV | 508 | 2027 | No
[6 empty] | 25INR0229 | OCI Cobb Creek Solar | Hill | 2027-12-31 | 2024-07-24 | Solar | PV | 203.1 | 2027 | Yes
[6 empty] | 25INR0482 | Vault Solar | Palo Pinto | 2027-12-31 | 2026-06-30 | Solar | PV | 108.5 | 2027 | Yes
[6 empty] | 27INR0127 | Bigway Solar I | King | 2027-12-31 | 2025-02-15 | Solar | PV | 195.2 | 2027 | Yes
[6 empty] | 27INR0128 | Bigway Solar II | King | 2027-12-31 | 2025-02-15 | Solar | PV | 206 | 2027 | Yes
[6 empty] | 25INR0430 | Hackberry Creek Solar | Mitchell | 2028-01-01 | 2025-12-02 | Solar | PV | 175.51 | 2028 | Yes
[6 empty] | 25INR0174 | Concho Pearl Solar | Concho | 2028-01-09 | 2024-07-22 | Solar | PV | 171.9 | 2028 | No
[6 empty] | 20INR0255 | Renegade Project | Deaf Smith | 2028-01-15 | 2021-01-04 | Solar | PV | 515.66 | 2028 | Yes
[6 empty] | 23INR0091 | Cascade Solar | Brazoria | 2028-01-15 | 2023-04-17 | Solar | PV | 171 | 2028 | Yes
[6 empty] | 24INR0440 | Starling Solar | Gonzales | 2028-01-28 | 2026-02-17 | Solar | PV | 144.6 | 2028 | No
[6 empty] | 20INR0086 | Arroyo Solar | Cameron | 2028-02-22 | 2021-09-28 | Solar | PV | 100 | 2028 | Yes
[6 empty] | 25INR0170 | Pinewood Solar | Brazoria | 2028-02-29 | 2025-05-08 | Solar | PV | 150.68 | 2028 | No
-62634.13

## Battery Chart
[6 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[6 empty] | 25INR0688 | Giga Texas Data Center | Travis | 2025-12-15 | 2025-04-30 | Battery | BA | 133 | 2025 | No
[6 empty] | 22INR0504 | Barton Branch IA | Robertson | 2026-10-01 | 2025-06-18 | Battery | BA | 203.62 | 2026 | Yes
[6 empty] | 25INR0231 | Apache Hill BESS | Hood | 2026-10-31 | 2024-06-26 | Battery | BA | 201.15 | 2026 | Yes
[6 empty] | 26INR0636 | Lyra Storage | Borden | 2026-11-12 | 2025-08-13 | Battery | BA | 500 | 2026 | No
[6 empty] | 25INR0133 | Rose Quartz BESS | Dimmit | 2026-12-01 | 2026-07-28 | Battery | BA | 101.41 | 2026 | No
[6 empty] | 26INR0375 | Avalon BESS | Fort Bend | 2026-12-01 | 2024-12-17 | Battery | BA | 522.12 | 2026 | No
[6 empty] | 22INR0503 | Tidwell Prairie II Batt | Robertson | 2026-12-03 | 2025-01-13 | Battery | BA | 203.62 | 2026 | Yes
[6 empty] | 20INR0246 | Ryan Energy Storage | Coryell | 2026-12-12 | 2021-02-18 | Battery | BA | 51.6 | 2026 | Yes
[6 empty] | 22INR0558 | Callisto II Energy Center | Harris | 2026-12-17 | 2023-12-11 | Battery | BA | 203.2 | 2026 | Yes
[6 empty] | 28INR0154 | Pamela Heights I | Harris | 2026-12-18 | 2025-10-07 | Battery | BA | 101.65 | 2026 | Yes
[6 empty] | 26INR0250 | Duffy BESS | Matagorda | 2026-12-31 | 2025-07-28 | Battery | BA | 241.05 | 2026 | Yes
[6 empty] | 25INR0101 | Drake BESS | Collin | 2027-01-29 | 2025-05-06 | Battery | BA | 257.3 | 2027 | Yes
[6 empty] | 24INR0210 | Raven Storage | Wharton | 2027-02-01 | 2024-06-04 | Battery | BA | 103.53 | 2027 | Yes
[6 empty] | 24INR0274 | Bufflehead BESS | Collin | 2027-02-15 | 2024-04-10 | Battery | BA | 153.77 | 2027 | No
[6 empty] | 25INR0271 | City Breeze BESS | Matagorda | 2027-03-18 | 2024-05-15 | Battery | BA | 143.1 | 2027 | Yes
[6 empty] | 26INR0201 | Rock Rose BESS | Fort Bend | 2027-03-19 | 2024-06-15 | Battery | BA | 208.5 | 2027 | Yes
[6 empty] | 24INR0136 | Eagle Springs Storage | Delta | 2027-03-29 | 2024-04-17 | Battery | BA | 33.94 | 2027 | Yes
[6 empty] | 24INR0155 | Lupinus Storage 2 | Franklin | 2027-04-03 | 2025-03-04 | Battery | BA | 124.55 | 2027 | Yes
[6 empty] | 24INR0472 | Amador Storage | Van Zandt | 2027-04-08 | 2023-11-02 | Battery | BA | 102.41 | 2027 | Yes
[6 empty] | 25INR0616 | Bobcat Bluff Storage SLF | Archer | 2027-04-15 | 2026-01-12 | Battery | BA | 0 | 2027 | No
[6 empty] | 26INR0296 | Sherbino II BESS SLF | Pecos | 2027-04-19 | 2024-08-01 | Battery | BA | 77.37 | 2027 | Yes
[6 empty] | 23INR0331 | Orange Grove BESS | Jim Wells | 2027-04-30 | 2022-11-30 | Battery | BA | 61.39 | 2027 | Yes
[6 empty] | 25INR0432 | Brotherton Storage | Anderson | 2027-05-01 | 2024-08-06 | Battery | BA | 176.13 | 2027 | Yes
[6 empty] | 23INR0392 | Honeycomb Storage SLF | Bee | 2027-05-11 | 2023-05-01 | Battery | BA | 0 | 2027 | Yes
[6 empty] | 25INR0301 | Van Zandt Energy Storage | Ector | 2027-05-15 | 2025-03-03 | Battery | BA | 256 | 2027 | No
[6 empty] | 26INR0340 | SOUTHERN SELECT ENERGY STORAGE | Galveston | 2027-05-24 | 2025-05-09 | Battery | BA | 204.85 | 2027 | Yes
[6 empty] | 25INR0189 | Staccato BESS | Fayette | 2027-05-28 | 2024-08-27 | Battery | BA | 201.8 | 2027 | Yes
[6 empty] | 22INR0239 | Rockefeller Storage | Schleicher | 2027-06-01 | 2024-09-23 | Battery | BA | 206.8 | 2027 | Yes
[6 empty] | 23INR0421 | Bee Branch IA | Robertson | 2027-06-01 | 2026-03-13 | Battery | BA | 203.75 | 2027 | Yes
[6 empty] | 25INR0235 | Austin Bayou Storage I | Brazoria | 2027-06-01 | 2025-02-14 | Battery | BA | 150.68 | 2027 | No
[6 empty] | 25INR0236 | Austin Bayou Storage II | Brazoria | 2027-06-01 | 2025-02-14 | Battery | BA | 156.6 | 2027 | No
[6 empty] | 25INR0237 | Austin Bayou Storage III | Brazoria | 2027-06-01 | 2025-02-14 | Battery | BA | 156.6 | 2027 | No
[6 empty] | 24INR0355 | Anatole Renewable Energy Storage | Henderson | 2027-06-30 | 2024-05-10 | Battery | BA | 207.82 | 2027 | Yes
[6 empty] | 26INR0385 | Nanulak BESS | Reeves | 2027-06-30 | 2025-11-19 | Battery | BA | 181.54 | 2027 | No
[6 empty] | 22INR0552 | Sowers Storage | Kaufman | 2027-07-01 | 2022-04-22 | Battery | BA | 208.89 | 2027 | Yes
[6 empty] | 26INR0034 | Bracero Pecan Storage | Reeves | 2027-07-01 | 2024-06-27 | Battery | BA | 238.21 | 2027 | Yes
[6 empty] | 23INR0232 | Hoke Storage | Gonzales | 2027-07-05 | 2022-04-25 | Battery | BA | 33.17 | 2027 | Yes
[6 empty] | 25INR0473 | Crowded Star I BESS | Jones | 2027-07-09 | 2025-12-01 | Battery | BA | 202.69 | 2027 | Yes
[6 empty] | 25INR0334 | Star Dairy Storage | Lamar | 2027-07-12 | 2024-12-09 | Battery | BA | 205.24 | 2027 | No
[6 empty] | 25INR0417 | Mesa View Storage | Upton | 2027-07-15 | 2024-09-09 | Battery | BA | 254.88 | 2027 | Yes
[6 empty] | 25INR0131 | SOSA Storage | Madison | 2027-07-20 | 2023-12-05 | Battery | BA | 154.63 | 2027 | Yes
[6 empty] | 24INR0386 | Black & Gold Energy Storage | Menard | 2027-07-30 | 2024-08-14 | Battery | BA | 203.8 | 2027 | Yes
[6 empty] | 25INR0253 | Whiskey BESS | Van Zandt | 2027-07-31 | 2025-03-28 | Battery | BA | 153.72 | 2027 | No
[6 empty] | 26INR0156 | Ross Storage | Refugio | 2027-07-31 | 2024-06-27 | Battery | BA | 510.99 | 2027 | No
[6 empty] | 25INR0442 | Happy Dog Storage | Milam | 2027-08-04 | 2024-12-16 | Battery | BA | 104.52 | 2027 | No
[6 empty] | 24INR0196 | Dori BQ BESS | Harris | 2027-08-30 | 2023-05-31 | Battery | BA | 154 | 2027 | No
[6 empty] | 25INR0384 | Zorro BESS | Van Zandt | 2027-08-31 | 2025-03-28 | Battery | BA | 153.69 | 2027 | No
[6 empty] | 23INR0342 | Brizo BESS | Victoria | 2027-09-01 | 2025-03-27 | Battery | BA | 144.22 | 2027 | No
[6 empty] | 27INR0173 | Trenno BESS | Johnson | 2027-09-13 | 2025-08-18 | Battery | BA | 202.56 | 2027 | No
[6 empty] | 25INR0122 | Vial BESS | Hill | 2027-09-15 | 2025-08-04 | Battery | BA | 135.18 | 2027 | Yes
[6 empty] | 24INR0496 | Indigo Storage | Fisher | 2027-09-17 | 2026-03-27 | Battery | BA | 60 | 2027 | Yes
[6 empty] | 25INR0528 | Indigo Storage 2 | Fisher | 2027-09-17 | 2026-03-27 | Battery | BA | 60 | 2027 | Yes
[6 empty] | 25INR0529 | Indigo Storage 3 | Fisher | 2027-09-17 | 2026-03-27 | Battery | BA | 60 | 2027 | Yes
[6 empty] | 25INR0530 | Indigo Storage 4 | Fisher | 2027-09-17 | 2026-03-27 | Battery | BA | 60 | 2027 | Yes
[6 empty] | 26INR0330 | Alamo City BESS | Bexar | 2027-09-21 | 2025-05-22 | Battery | BA | 128.2 | 2027 | No
[6 empty] | 26INR0033 | Fairway Storage | Freestone | 2027-09-24 | 2025-08-11 | Battery | BA | 120.3 | 2027 | Yes
[6 empty] | 23INR0140 | Seine BESS | Foard | 2027-10-01 | 2024-12-01 | Battery | BA | 308.88 | 2027 | Yes
[6 empty] | 24INR0392 | Riverwalk BESS | Bexar | 2027-10-01 | 2026-08-18 | Battery | BA | 120 | 2027 | No
Month/Year | Cumulative operational, No FS, and FS Posted | Cumulative MW Operational | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Small Generator | 27INR0440 | Wisdom BESS SLF | Pecos | 2027-10-06 | 2026-03-18 | Battery | BA | 102.88 | 2027 | No
2026-09-20 | 21669.67 | 21536.67 | 0 | 133 | 0 | 25INR0480 | Bell Creek BESS | Brazoria | 2027-10-30 | 2024-11-14 | Battery | BA | 200.9 | 2027 | No
2026-10-20 | 22074.44 | 21536.67 | 404.77 | 133 | 0 | 26INR0314 | Brazos River BESS | Brazoria | 2027-10-30 | 2025-05-24 | Battery | BA | 180.36 | 2027 | No
2026-11-20 | 22613.24 | 21536.67 | 404.77 | 633 | 38.8 | 26INR0131 | Elm Flats Storage SLF | Navarro | 2027-11-01 | 2025-11-21 | Battery | BA | 0 | 2027 | Yes
2026-12-20 | 24057.78 | 21536.67 | 1205.89 | 1256.53 | 58.69 | 26INR0226 | First Capitol BESS | Brazoria | 2027-11-01 | 2025-05-15 | Battery | BA | 257.48 | 2027 | Yes
2027-01-20 | 24330.57 | 21536.67 | 1463.19 | 1256.53 | 74.18 | 25INR0375 | NavBoot BESS | Nueces | 2027-11-11 | 2025-10-20 | Battery | BA | 303.7 | 2027 | No
2027-02-20 | 24607.67 | 21536.67 | 1566.72 | 1410.3 | 93.98 | 24INR0281 | Red Egret BESS | Galveston | 2027-11-17 | 2023-06-07 | Battery | BA | 310.58 | 2027 | Yes
2027-03-20 | 25013.19 | 21536.67 | 1952.26 | 1410.3 | 113.96 | 22INR0457 | Anson BAT | Jones | 2027-12-01 | 2024-08-15 | Battery | BA | 153.55 | 2027 | Yes
2027-04-20 | 25378.91 | 21536.67 | 2317.98 | 1410.3 | 113.96 | 23INR0290 | Zeya BESS | Galveston | 2027-12-01 | 2023-01-20 | Battery | BA | 255.33 | 2027 | Yes
2027-05-20 | 26217.69 | 21536.67 | 2900.76 | 1666.3 | 113.96 | 25INR0169 | Piedra BESS | Freestone | 2027-12-01 | 2024-07-02 | Battery | BA | 103.65 | 2027 | Yes
2027-06-20 | 27481.48 | 21536.67 | 3519.13 | 2311.72 | 113.96 | 26INR0474 | Sorghum BESS | Wharton | 2027-12-01 | 2025-01-08 | Battery | BA | 208.9 | 2027 | No
2027-07-20 | 29647.7 | 21536.67 | 4815.4 | 3181.67 | 113.96 | 27INR0485 | Blackland Prairie 1 Energy Storage | Travis | 2027-12-01 | 2026-04-10 | Battery | BA | 102.1 | 2027 | No
2027-08-20 | 30069.9 | 21536.67 | 4815.4 | 3593.88 | 123.95 | 25INR0230 | Great Rock BESS | Leon | 2027-12-20 | 2024-08-23 | Battery | BA | 300.9 | 2027 | No
2027-09-20 | 31040.36 | 21536.67 | 5310.88 | 4068.86 | 123.95 | 21INR0444 | Long Point Storage | Brazoria | 2027-12-30 | 2023-08-28 | Battery | BA | 100.62 | 2027 | No
2027-10-20 | 31953.38 | 21536.67 | 5619.76 | 4673 | 123.95 | 23INR0216 | Venus Mill Storage | Ellis | 2027-12-31 | 2025-12-24 | Battery | BA | 100.8 | 2027 | No
2027-11-20 | 32825.14 | 21536.67 | 6187.82 | 4976.7 | 123.95 | 25INR0371 | McMurtre Storage | Hunt | 2027-12-31 | 2025-09-17 | Battery | BA | 176.13 | 2027 | Yes
2027-12-20 | 34818.2 | 21536.67 | 7077.56 | 6080.02 | 123.95 | 25INR0441 | Dios BESS | Jackson | 2027-12-31 | 2025-04-03 | Battery | BA | 201.08 | 2027 | Yes
2028-01-20 | 35712.94 | 21536.67 | 7391.3 | 6661.02 | 123.95 | 25INR0451 | Tres Rios Ranch BESS | Upton | 2027-12-31 | 2025-12-30 | Battery | BA | 290 | 2027 | No
2028-02-20 | 36757.38 | 21536.67 | 8179.4 | 6917.36 | 123.95 | 24INR0178 | Cumulus Grid BESS | Ellis | 2028-01-01 | 2025-06-03 | Battery | BA | 210.74 | 2028 | Yes
[6 empty] | 26INR0417 | GAMAY ENERGY STORAGE | Brazoria | 2028-01-01 | 2025-05-27 | Battery | BA | 418.6 | 2028 | No
[6 empty] | 25INR0175 | Concho Pearl Storage | Concho | 2028-01-09 | 2024-07-22 | Battery | BA | 162.4 | 2028 | No
[6 empty] | 23INR0137 | Diran BESS | Wharton | 2028-01-31 | 2025-01-07 | Battery | BA | 103 | 2028 | Yes
[6 empty] | 25INR0391 | Purple Sage BESS 1 | Collin | 2028-02-12 | 2024-10-11 | Battery | BA | 156 | 2028 | Yes
[6 empty] | 25INR0392 | Purple Sage BESS 2 | Collin | 2028-02-12 | 2024-10-11 | Battery | BA | 156 | 2028 | Yes
[6 empty] | 26INR0551 | Hastings Park BESS | Brazoria | 2028-02-27 | 2025-08-13 | Battery | BA | 256.34 | 2028 | No
[6 empty] | 23INR0425 | Coneflower Storage Project | Chambers | 2028-02-28 | 2024-03-25 | Battery | BA | 170.85 | 2028 | Yes
[6 empty] | 26INR0189 | Skipjack Energy Storage | Brazoria | 2028-02-28 | 2024-08-13 | Battery | BA | 150.6 | 2028 | Yes
[6 empty] | 24INR0425 | Two Brothers ESS | Victoria | 2028-02-29 | 2024-04-22 | Battery | BA | 154.65 | 2028 | Yes
Small Generators
[6 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[6 empty] | 25INR0601 | East Bernard BESS | Wharton | 2026-11-04 | 2024-04-29 | Battery | BA | 9.5 | 2026 | Yes
[6 empty] | 25INR0604 | Pledger BESS | Matagorda | 2026-11-04 | 2024-04-29 | Battery | BA | 9.5 | 2026 | Yes
[6 empty] | 25INR0768 | Stafford Hill BESS | Colorado | 2026-11-14 | 2026-05-28 | Battery | BA | 9.9 | 2026 | Yes
[6 empty] | 26INR0574 | Apple BESS | Ector | 2026-11-27 | 2025-04-03 | Battery | BA | 9.9 | 2026 | Yes
[6 empty] | 25INR0769 | Kleimann BESS | Colorado | 2026-12-08 | 2025-03-31 | Battery | BA | 9.9 | 2026 | Yes
[6 empty] | 26INR0714 | Pavlov BESS2 | Matagorda | 2026-12-13 | 2025-06-18 | Battery | BA | 9.99 | 2026 | Yes
[6 empty] | 24INR0712 | Byrd Ranch Repower | Brazoria | 2027-01-22 | 2020-12-14 | Battery | BA | 5.5 | 2027 | No
[6 empty] | 26INR0702 | Bexar Martinez BESS | Bexar | 2027-01-23 | 2026-02-03 | Battery | BA | 9.99 | 2027 | Yes
[6 empty] | 26INR0773 | Seaway BESS | Waller | 2027-02-22 | 2024-12-11 | Battery | BA | 9.9 | 2027 | Yes
[6 empty] | 26INR0774 | Wallis BESS2 | Austin | 2027-02-22 | 2024-12-11 | Battery | BA | 9.9 | 2027 | Yes
[6 empty] | 25INR0602 | Hockley BESS | Harris | 2027-03-01 | 2024-04-29 | Battery | BA | 9.99 | 2027 | Yes
[6 empty] | 26INR0734 | Alamo Street BESS2 | Pecos | 2027-03-30 | 2023-02-01 | Battery | BA | 9.99 | 2027 | Yes
[6 empty] | 23INR0603 | Damon BESS 2 | Brazoria | 2027-08-21 | 2023-10-06 | Battery | BA | 9.99 | 2027 | Yes

## Gas-Combined Cycle Chart
[6 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[6 empty] | 20INR0286 | Wise County Power Repower (CT1, CT2) | Wise | 2026-12-19 | 2001-03-19 | Gas | CC | 21 | 2026 | Yes
Month/Year | Cumulative operational, No FS, and FS Posted | Cumulative MW Operational | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Small Generator
2026-09-20 | 44025.609 | 44025.609 | 0 | 0 | 0
2026-10-20 | 44025.609 | 44025.609 | 0 | 0 | 0
2026-11-20 | 44025.609 | 44025.609 | 0 | 0 | 0
2026-12-20 | 44046.609 | 44025.609 | 21 | 0 | 0
2027-01-20 | 44046.609 | 44025.609 | 21 | 0 | 0
2027-02-20 | 44046.609 | 44025.609 | 21 | 0 | 0
2027-03-20 | 44046.609 | 44025.609 | 21 | 0 | 0
2027-04-20 | 44046.609 | 44025.609 | 21 | 0 | 0
2027-05-20 | 44046.609 | 44025.609 | 21 | 0 | 0
2027-06-20 | 44046.609 | 44025.609 | 21 | 0 | 0
2027-07-20 | 44046.609 | 44025.609 | 21 | 0 | 0
2027-08-20 | 44046.609 | 44025.609 | 21 | 0 | 0
2027-09-20 | 44046.609 | 44025.609 | 21 | 0 | 0
2027-10-20 | 44046.609 | 44025.609 | 21 | 0 | 0
2027-11-20 | 44046.609 | 44025.609 | 21 | 0 | 0
2027-12-20 | 44046.609 | 44025.609 | 21 | 0 | 0
2028-01-20 | 44046.609 | 44025.609 | 21 | 0 | 0
2028-02-20 | 44046.609 | 44025.609 | 21 | 0 | 0

## Gas-Other Chart
[7 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[7 empty] | 26INR0111 | Graphic Packaging Gas | McLennan | 2027-02-15 | 2026-07-30 | Gas | GT | 43.36 | 2027 | Yes
[7 empty] | 27INR0181 | Elk Unit 4 | Hale | 2027-02-28 | 2025-12-30 | Gas | GT | 210 | 2027 | Yes
[7 empty] | 26INR0261 | Bastrop Peaking Generators (TEF-Due Diligence) | Bastrop | 2027-12-07 | 2025-12-19 | Gas | GT | 1104 | 2027 | No
[7 empty] | 28INR0089 | EmberYork | Austin | 2028-01-01 | 2025-12-12 | Gas | GT | 900 | 2028 | No
[7 empty] | 28INR0090 | EmberGreen | Wharton | 2028-01-01 | 2026-08-04 | Gas | GT | 1036 | 2028 | No
[7 empty] | 28INR0108 | RAYBURN ENERGY STATION II Gas (TEF-Due Diligence) | Grayson | 2028-02-26 | 2025-12-22 | Gas | GT | 570 | 2028 | Yes
Month/Year | Cumulative operational, No FS, and FS Posted | Cumulative MW Operational | IA Signed-Financial Security Posted | IA Signed-No Financial Security | Other Planned | Small Generator
2026-09-20 | 25383.55 | 25333.96 | 0 | 0 | 49.59 | 0
2026-10-20 | 25383.55 | 25333.96 | 0 | 0 | 49.59 | 0
2026-11-20 | 25383.55 | 25333.96 | 0 | 0 | 49.59 | 0
2026-12-20 | 25391.35 | 25333.96 | 0 | 0 | 57.39 | 0
2027-01-20 | 25391.35 | 25333.96 | 0 | 0 | 57.39 | 0
2027-02-20 | 25644.71 | 25333.96 | 253.36 | 0 | 57.39 | 0
2027-03-20 | 25654.7 | 25333.96 | 253.36 | 0 | 67.38 | 0
2027-04-20 | 25654.7 | 25333.96 | 253.36 | 0 | 67.38 | 0
2027-05-20 | 25654.7 | 25333.96 | 253.36 | 0 | 67.38 | 0
2027-06-20 | 25654.7 | 25333.96 | 253.36 | 0 | 67.38 | 0
2027-07-20 | 25664.69 | 25333.96 | 253.36 | 0 | 77.37 | 0
2027-08-20 | 25664.69 | 25333.96 | 253.36 | 0 | 77.37 | 0
2027-09-20 | 25674.68 | 25333.96 | 253.36 | 0 | 87.36 | 0
2027-10-20 | 25674.68 | 25333.96 | 253.36 | 0 | 87.36 | 0
2027-11-20 | 25674.68 | 25333.96 | 253.36 | 0 | 87.36 | 0
2027-12-20 | 26778.68 | 25333.96 | 253.36 | 1104 | 87.36 | 0
2028-01-20 | 28714.68 | 25333.96 | 253.36 | 3040 | 87.36 | 0
2028-02-20 | 29284.68 | 25333.96 | 823.36 | 3040 | 87.36 | 0